Cross-Cutting Tool - 6

Cohort Review Preparation: 
Roles and Responsibilities by Time Due

| Timeline | Job Role | Responsibility |
| --- | --- | --- |
| 12 weeks prior | Admin | Organizes room and AV equipment |
| 6 weeks prior | Epidemiologist | 1) Identifies cohort period, pulls data, and ensures that NTIP and cohort measures are up-to-date 2) Provides list of cases to Nurse Case Managers for Mock cohort 3) Runs case, contact and NTIP reports and analyses 4) Fixes data issues 5) Follow-up with leads if particular issues were identified at last cohort |
|  | Nursing Supervisor/Lead Nurse | Provides list of needed case charts to Admin |
|  | Admin | Pulls needed case charts for nurse case managers/DRDS |
| 5 weeks prior | Epidemiologist | 1) Prepares list of issues/challenges/success along with potential cases and gives to nursing supervisor for distribution 2) Provides new clean list once to Nurse case managers once feedback has been received 3) Updates RVCTS, NTIP data 4) Reviews Cohort/NTIP issues identified with management team |
|  | Nursing Supervisor/Lead Nurse | Identifies those cases that may be of interest for discussion at cohort (based on Epi list) |
|  | Nurse Case Manager | Prepares cases of interest for cohort review. Addresses indicators. |
| 4 weeks prior | Epidemiologist | Prepares cohort review presentation list based on PHIMS data |
|  | DIS | Prepares cohort review presentation list contact investigation updates |
|  | CDC | Provides updated NTIP summaries; RVCT #’s for those cases not meeting indicators |
| 3 weeks prior | Epidemiologist | 1) Prepares genotyping summary and looks for clusters 2) Updates cohort issues log from last cohort |
|  | Nursing Supervisor/Lead Nurse | Meets with Nurse case managers to discuss cases of interest and work on presentation |
|  | Nurse Case Manager | Provides feedback to Epi on issues raised; Works with DIS on contact summaries as needed; reviews cohort presentation list for accuracy |
|  | Program Manager | Prepares slides on overall cohort objectives, specific targets for this particular cohort, and successes and challenges that will be discussed |
|  | DIS | Works with Nurse Case Manager to prepare contact summaries |
|  | Outreach Worker | Works with Nurse Case Manager to prepare DOT issues |
| 2 weeks prior | Epidemiologist | 1) Participates in mock cohort review 2) Shares genotypes with DOH and vice versa 3) Finalizes indicators |
|  | Nursing Supervisor/Lead Nurse | - Participates in mock cohort review - Identifies cases to be presented |
|  | Nurse Case Manager | Participates in mock cohort review |
|  | Program Manager | Participates in mock cohort review |
|  | DIS | 1)Participates in mock cohort review 2)Ensures contact investigation data and binders are up to date |
|  | Outreach Worker | Participates in mock cohort review |
|  | DRDS | Updates RVCTs with corrected data if incorrect in NTIP |
|  | CDC | Updates NTIP with latest data |
| Day of cohort review | Admin | 1)Sets up computer, projector, and screen for presentation 2) Takes notes on cohort issues |
|  | Epidemiologist | Presents cohort case, contact, and NTIP data summaries |
|  | Nurse Case Manager | Presents cases and indicators met |
|  | Program Manager | 1) Facilitates case discussions and program assessment. 2) Reviews list of issues and challenges and identifies leads. |
|  | DIS | Presents cases with relevant contact investigations |
|  | Outreach Worker | Presents cases with relevant DOT issues |
|  | Medical Director/Health Officer | Facilitates case discussions as needed |
|  | DRDS | Reviews open RVCTs and checks data as needed |